# Workforce Planning Model – Concepts, Logic, and Formulas

This document provides a step-by-step conceptual framework and formulas to design a comprehensive workforce planning and staffing capacity model. It is tool-agnostic and can be implemented in Excel, Python/Dash, Power BI, or other analytics platforms. The goal is to assess whether staffing levels are sufficient to meet assigned and projected work over a 12‑month horizon.

## 1. Planning Structure and Time Horizon

Planning is performed at a monthly level for the next 12 months. Monthly granularity balances forecast accuracy with usability and aligns well with project timelines, hiring decisions, and budgeting.

### Key entities

• Staff (name, role, FTE, availability assumptions)
• Time (months)
• Work demand (fixed, assigned, variable)
• Capacity (available working time)

## 2. Capacity (Supply) Modeling

### 2.1 Base Working Capacity

Base capacity represents the theoretical maximum working time before accounting for interruptions, overhead, or leave.

Formula:

BaseCapacityHours = WorkingDays × (WorkdayHours − LunchBreakHours) × FTE

Insights:

• Use business days rather than calendar days
• Lunch and mandatory breaks should be removed to avoid overstating capacity
• FTE allows part-time staff to be modeled consistently

### 2.2 Overhead and Non-Productive Time

Not all working hours are available for delivery. Overhead includes email, coordination, admin work, context switching, and informal interruptions.

Primary approach (percentage-based):

OverheadHours = BaseCapacityHours × OverheadFactor
NetCapacityHours = BaseCapacityHours − OverheadHours

Alternative approach (task-based):

Explicitly model recurring admin tasks as fixed demand instead of a percentage.

Pros & Cons:

• Percentage-based: Simple, scalable, but less transparent
• Task-based: More accurate, but higher data maintenance effort

### 2.3 Planned Time Off (PTO)

Planned leave reduces available capacity and should be included explicitly.

Approximate formula:

PTOHoursPerMonth = (AnnualPTODays ÷ 12) × (WorkdayHours − LunchBreakHours) × FTE

Alternative:

Input PTO at a monthly or individual level for higher accuracy.

### Final Net Capacity Formula

NetCapacityHours = BaseCapacityHours − OverheadHours − PTOHours

## 3. Demand (Workload) Modeling

### 3.1 Fixed (Sunk) Commitments

Fixed commitments are recurring obligations that exist regardless of project load (committees, training, governance, meetings).

Formula per task:

MonthlyTaskHours = HoursPerOccurrence × FrequencyMultiplier

Typical frequency multipliers:

• Weekly: 4.33
• Monthly: 1.0
• Quarterly: 0.33
• Annual: 0.08

FixedDemandHours per person is the sum of applicable tasks.

### 3.2 Assigned Projects (Committed Work)

Assigned projects represent confirmed demand with known start and end dates.

Method A: Spread total hours evenly

ProjectMonthlyHours = TotalProjectHours ÷ ProjectDurationMonths

Method B: Fixed monthly estimate

ProjectMonthlyHours = ProvidedMonthlyEstimate

Method C: FTE allocation

ProjectMonthlyHours = AllocationPercent × NetCapacityHours

Pros & Cons:

• Total-hours spread: Easy but ignores ramp-up and peaks
• Monthly estimates: More accurate but harder to forecast
• FTE allocation: Useful early, but self-referential to capacity

### 3.3 Variable / Expected Work

Variable work includes expected inflow such as small projects, requests, or reactive tasks.

Formula (team-level):

VariableDemandHours = Σ (ExpectedVolume × StandardHoursPerUnit)

Allocation options:

• Pooled allocation using predefined staff shares
• Allocation by role/skill mix
• Allocation based on remaining capacity (iterative)

Insight:

Variable work is the primary lever for breakeven and scenario testing.

## 4. Utilization and Capacity Fit

### 4.1 Individual Utilization

Utilization indicates workload pressure at the individual level.

Formula:

Utilization = TotalDemandHours ÷ NetCapacityHours

Guidance:

• Sustained utilization above ~85–90% increases delivery risk
• Persistent under-utilization suggests overcapacity or misallocation

### 4.2 Team Utilization

Team utilization aggregates pressure across all staff.

TeamUtilization = TotalTeamDemandHours ÷ TotalTeamCapacityHours

## 5. Headcount / FTE Gap Calculation

This is the core output: whether you have the right number of people.

Step 1: Productive hours per FTE

ProdHoursPerFTE = TotalTeamCapacityHours ÷ AvailableFTE

Step 2: Required FTE

RequiredFTE = TotalTeamDemandHours ÷ (ProdHoursPerFTE × TargetUtilization)

Step 3: FTE Gap

FTEGap = RequiredFTE − AvailableFTE

Interpretation:

• Positive gap → staffing shortfall
• Negative gap → surplus capacity

## 6. Breakeven Analysis

Breakeven identifies how much variable work can be absorbed before additional hiring is required.

Formula:

BreakevenVariableHours = (TeamCapacityHours × TargetUtilization) − (Fixed + Assigned Demand)

BreakevenVolume = BreakevenVariableHours ÷ AverageStandardHoursPerUnit

## 7. Monthly Visual Outputs

Recommended dashboard visuals:

• Required vs Available FTE (line + bar)
• Team utilization over time
• Individual utilization lines
• Utilization heatmap (staff × month)

## 8. Advanced Factors Often Missed

• Role/skill constraints (non-interchangeable hours)
• Hiring ramp-up and onboarding time
• Context switching penalties with many parallel projects
• Carryover/backlog of unmet demand
• Seasonality and deadline spikes
• Demand uncertainty (low/base/high scenarios)
• Attrition risk and vacancy buffers

## 9. Design Philosophy

Start simple, validate assumptions, and layer complexity only where it materially improves decision quality. The most valuable models are transparent, explainable, and scenario-driven rather than perfectly precise.

## 1) Define the planning grain

Use a monthly time bucket for the next 12 months.

For each month m you’ll compute:

- CapacityHours[m] (how many productive hours you can supply)

- DemandHours[m] (how many hours of work you need)

- GapHours[m] = DemandHours[m] − CapacityHours[m]

- Convert gap to FTE / headcount.

## 2) Build your capacity model (supply)

### 2.1 Monthly working time per person

For each staff i and month m:

WorkingDays[i,m]

- If you have a holiday calendar:

  - WorkingDays = NETWORKDAYS(MonthStart, MonthEnd, Holidays)

- If not: approximate business days (e.g., 20–23 depending on month).

ProductiveHoursPerDay

- ProductiveHoursPerDay = WorkdayHours − LunchBreakHours

  - Example: 8 − 1 = 7

BaseCapacityHours[i,m]

- BaseCapacityHours = WorkingDays × ProductiveHoursPerDay × FTE[i]

### 2.2 Subtract “always happens” overhead + planned time off

You need to avoid assuming 100% of base hours are usable.

OverheadHours[i,m] (email, admin, context switching)

- simplest:

  - OverheadHours = BaseCapacityHours × OverheadFactor

  - Example overhead factor: 10–25% depending on role

PTOHours[i,m] (vacation/sick)
Two options:

- Approximate from annual PTO:

  - PTOHours = (PTO_DaysPerYear / 12) × ProductiveHoursPerDay × FTE

- Better: input PTO days per person per month:

  - PTOHours = PTO_Days[i,m] × ProductiveHoursPerDay

NetCapacityHours[i,m]

- NetCapacityHours = BaseCapacityHours − OverheadHours − PTOHours

- clip at zero if needed.

If you include some “admin” as fixed tasks later, reduce OverheadFactor to avoid double counting.

## 3) Build your demand model (workload)

Break demand into three buckets:

- Assigned/committed projects

- Variable work (expected inflow)

- Fixed sunk commitments (committees, training, recurring tasks)

### 3.1 Fixed sunk commitments (per person)

For each task t, define:

- HoursPerOccurrence[t]

- Frequency[t] (weekly/monthly/quarterly/annual)

- AppliesTo (All staff / role / specific person)

Convert frequency to monthly multiplier:

- Weekly: 4.33

- Monthly: 1

- Quarterly: 1/3

- Annual: 1/12

FixedTaskHoursPerMonth[t]

- FixedTaskHoursPerMonth = HoursPerOccurrence × FrequencyMultiplier

Then allocate to staff based on applicability:

FixedDemandHours[i,m]

- FixedDemandHours = Σ FixedTaskHoursPerMonth[t] for tasks that apply to staff i

(Usually constant across months unless some tasks are seasonal.)

### 3.2 Assigned/committed projects (per person)

Each assignment row should be:
Project p assigned to Person i with:

- StartDate[p,i]

- EndDate[p,i]

- Category[p] (simple/complex/targeted)

- RoleOnProject[p,i]

- effort estimate: either TotalHours or MonthlyHours or % allocation

Determine if project is active in month m:

- Active[p,i,m] = 1 if MonthStart[m] ≤ EndDate AND MonthEnd[m] ≥ StartDate else 0

Now choose an effort method:

#### Method A: Total hours spread across duration (simple & common)

Compute duration in months:

- DurationMonths = number of months between StartDate and EndDate (inclusive)

Monthly hours:

- ProjectHours[p,i,m] = Active × (TotalHours[p,i] / DurationMonths)

#### Method B: Monthly hours provided

- ProjectHours[p,i,m] = Active × MonthlyHours[p,i]

#### Method C: % allocation based (if you don’t estimate hours)

If you define AllocPct[p,i] (e.g. 0.3 FTE) for months active:

- ProjectHours[p,i,m] = Active × AllocPct[p,i] × NetCapacityHours[i,m]
This “self-references” capacity; it’s fine if you treat allocation as planned usage.

Then:
AssignedProjectDemand[i,m] = Σ ProjectHours[p,i,m]

### 3.3 Variable work (inflow / expected projects)

This is the breakeven knob.

Define categories c (simple/complex/targeted) with:

- StdHoursPerUnit[c]

- Volume[m,c] (expected number of projects/tasks in month m)

VariableDemandHoursTeam[m]

- VariableDemandHoursTeam[m] = Σ (Volume[m,c] × StdHoursPerUnit[c])

Now allocate variable work to people. Options:

#### Allocation option 1: Pooled share (fastest)

Each staff has VariableShare[i] where Σ shares = 1:

- VariableDemand[i,m] = VariableDemandHoursTeam[m] × VariableShare[i]

#### Allocation option 2: By role/skill (more realistic)

Split variable demand by role:

- decide RoleSplit[c,role] (e.g., Simple: 80% analyst, 20% PM)

- VariableDemandRole[m,role] = Σ Volume[m,c] × StdHoursPerUnit[c] × RoleSplit[c,role]
Then allocate within role by FTE or shares.

#### Allocation option 3: By remaining capacity (best, but iterative)

Allocate variable work to whoever has capacity left:

- Remaining[i,m] = NetCapacityHours[i,m] − FixedDemand − AssignedProjectDemand

- Distribute variable demand proportionally to remaining (clip negatives to 0)

## 4) Combine demand and compute utilization

For each person/month:

TotalDemandHours[i,m]

- TotalDemand = FixedDemand + AssignedProjectDemand + VariableDemand

Utilization[i,m]

- Utilization = TotalDemand / NetCapacityHours

Also compute:

- RemainingCapacity[i,m] = NetCapacityHours − TotalDemand

## 5) Team summary and “headcount fit” (your key output)

### 5.1 Team totals per month

- TeamCapacityHours[m] = Σ NetCapacityHours[i,m]

- TeamDemandHours[m] = Σ TotalDemandHours[i,m]

- TeamUtilization[m] = TeamDemandHours / TeamCapacityHours

### 5.2 Required FTE and FTE gap

You need a clean way to translate hours to headcount.

Compute “productive hours per 1.0 FTE” for that month:

- ProdHoursPerFTE[m] = TeamCapacityHours[m] / AvailableFTE[m]
where:

- AvailableFTE[m] = Σ FTE[i] (if headcount is stable)

Set a target utilization (because you don’t want to plan at 100%):

- TargetUtil (e.g., 0.80–0.90)

RequiredFTE[m]

- RequiredFTE = TeamDemandHours / (ProdHoursPerFTE × TargetUtil)

FTEGap[m]

- FTEGap = RequiredFTE − AvailableFTE

- If FTEGap > 0: you are short by that many FTE.

- If < 0: surplus.

If you want “headcount” not FTE:

- HeadcountGap ≈ FTEGap / AvgFTEPerEmployee

  - if most are full-time, AvgFTE≈1 so it’s basically the same.

## 6) Breakeven volumes (your toggle requirement)

You want to know “how many variable projects can we absorb?”

For month m:

- BreakevenVariableHours[m] = TeamCapacityHours[m] × TargetUtil − (AssignedProjectDemandTeam[m] + FixedDemandTeam[m])

Then per category:

- BreakevenVolume[m,c] = BreakevenVariableHours[m] / StdHoursPerUnit[c]
(if you assume only that category changes)

Or for a blended mix of categories, use weighted average standard time:

- AvgStdHours = Σ mix[c] × StdHoursPerUnit[c]

- BreakevenTotalVolume = BreakevenVariableHours / AvgStdHours

## 7) Monthly graphs to include (and what they show)

- Required FTE vs Available FTE (line + bars)

  - shows hiring shortfall/surplus by month

- Team utilization % trend

  - shows pressure and seasonality

- Individual utilization % lines

  - shows overload by person + when it happens

- Heatmap (people x months utilization)

  - fastest way to spot persistent overloads

## 8) Common missing factors to consider (pick the ones that matter)

These usually make models “real”:

- Role/skill constraints

  - compute RequiredFTE and gaps by role (PM vs Analyst etc.)

- Ramp-up for new hires

  - productivity curve (e.g., 50%, 75%, 90% across first 3 months)

- Context switching penalty

  - overhead factor increases with number of active projects

- Carryover/backlog

  - if Demand > Capacity, do you defer work into next month?

- Uncertainty

  - add low/base/high hours per project or category

- Non-PTO unavailability

  - sick leave, training blocks, conferences, parental leave

- Dependencies

  - some work cannot start until earlier tasks finish (affects timing)

## Minimal “starter” version I’d build first

If you want a simple version that still answers your question well:

- Capacity: workdays × (8−1) × FTE − 15% overhead − PTO

- Fixed tasks: monthly hours by role/all

- Projects: total hours spread across active months

- Variable: volumes × standard hours (with slider/scenario)

- Output: utilization + FTE gap monthly + individual utilization

Then add role-based gaps and carryover.

If you tell me your typical roles (e.g., PM/Analyst/Senior) and whether variable work is shared or handled by a subset, I’ll show you the exact role-based formulas (that’s the biggest leap in realism).